## Event Budget
Event Budget
Instructions: Make a copy and edit the fields highlighted in yellow.
Total Income | 9850
Total Expenses | 0
Event Profit | 9850
INCOME | [6 empty] | 26-27 TEAM Alliance In-Person Event Registration Fees
Registration Fees | # of Teams | Pre-Qualifying Event | # of Teams | Qualifying Event | # of Teams | Championship Event | Event Fees | Pre-Qualifying Event | Qualifying Event | Championship Event
SRM - indi | N/A | N/A | 12 | 600 | 12 | 840 | SRM - indi | N/A | 50 | 70
SRM - BOLT | N/A | N/A | 16 | 800 | 16 | 1120 | SRM - BOLT | N/A | 50 | 70
SRM - RVR | N/A | N/A | 12 | 600 | 12 | 840 | SRM - RVR | N/A | 50 | 70
SRC | 10 | 750 | 10 | 1100 | 20 | 3200 | SRC | 75 | 110 | 160
Sub-Total |  | 750 |  | 3100 |  | 6000
Other Income | Estimated Income
Concessions | 0
Sponsorships | 0
Other | 0
Sub-Total | 0
Expenses
Competition Fields | Cost | Quantity | Total | Notes
SRM - indi Fields (4-pack) | 120 | 1 | 0 | (1) 4-Pack free with Event Support Package. This provides enough for (2) indi Competition Fields
SRM - BOLT Field | 189 | 2 | 0 | (2) Fields free with Event Support Package
SRM - RVR Field | 300 | 2 | 0 | (2) Fields free with Event Support Package
SRC Field | 999 | 2 | 0 | (2) Fields free with Event Support Package
SRC 26-27 Game Element Kit | 399 | 2 | 0 | (2) Game Element Kits free with Event Support Package
Sub-Total |  |  | 0
Event Equipment | Cost | Quantity | Total | Notes
Qualifying Event Trophies / Medals | 0 | 1 | 0 | (1) Set free with Event Support Package
Championship Event Trophies / Medals | 0 | 1 | 0 | (1) Set free with Event Support Package
SRC Sizing Tool | 0 | 1 | 0 | (1) Set free with Event Support Package
TEAM Alliance Event Signage | 0 | 1 | 0 | (1) Free with Event Support Package
TEAM Alliance / Sphero Swag | 0 | 1 | 0 | (1) Free with Event Support Package
Sub-Total |  |  | 0
Venue Expenses | Cost | Quantity | Total | Notes
Rental / Facility Fee | 0 | 0 | 0
Custodial Fees | 0 | 0 | 0
Event Insurance | 0 | 0 | 0
Chair / Table Rental | 0 | 0 | 0
Laptops | 0 | 0 | 0
Tablets | 0 | 0 | 0
Tablet Charging Station | 0 | 0 | 0
Speakers / Microphone | 0 | 0 | 0
Large Displays / Projector & Screens | 0 | 0 | 0
Extension Cords | 0 | 0 | 0
Printer/Paper/Toner | 0 | 0 | 0
Clipboards / Pens | 0 | 0 | 0
Additional Event Signage | 0 | 0 | 0
Concession Supplies | 0 | 0 | 0
Sub-Total |  |  | 0
Volunteer Supplies | Cost | Quantity | Total | Notes
Referee / Evaluator Shirts | 0 | 0 | 0
Volunteer Shirts | 0 | 0 | 0
Food / Drink / Snacks | 0 | 0 | 0
Sub-Total |  |  | 0
Other Miscellaneous Expenses | Cost | Quantity | Total | Notes
[Edit] | 0 | 0 | 0
[Edit] | 0 | 0 | 0
[Edit] | 0 | 0 | 0
Sub-Total |  |  | 0

## Event Agendas
NEW: Interactive Event Agenda Web Tool:
www.teamalliance.org/agenda-builder
Use the web tool to create an agenda, then copy/paste it into your event page.
Note: The Event Agenda Web Tool is based on this spreadsheet, but is much easier to use. For now, we are leaving this portion of the spreadsheet for reference only, but it's recommended to use the Event Agenda Web Tool instead.
SRM Event Agenda | [6 empty] | SRC Event Agenda
SRM Events | Qualifying Event |  |  | Championship Event |  |  | SRC Events | Qualifying Event | Championship Event |  | SRC Cycle Times (minutes)
| SRM - indi | SRM - BOLT | SRM - RVR | SRM - indi | SRM - BOLT | SRM - RVR |  | SRC | SRC |  | 1 Field | 2+ Fields
# Teams | 12 | 16 | 12 | 12 | 16 | 12 | # Teams | 8 | 20 |  | 6 | 4
# Missions per Team | 2 | 3 | 3 | 3 | 4 | 4 | Matches
Mission Cycle Time (minutes) | 10 | 10 | 10 | 10 | 10 | 10 | # Matches / Team | 6 | 6 |  | Finals Bracket Matches
Break Time Between Missions (minutes) | 10 | 10 | 10 | 10 | 10 | 10 | Match Cycle Time (minutes) | 6 | 4 |  | 16+ Teams | 15
Fields | 2 | 2 | 2 | 2 | 2 | 2 | Match Fields | 1 | 2 |  | 12-15 Teams | 11
Total Mission Time (minutes) | 140 | 270 | 210 | 210 | 360 | 280 | Match Time - Per Heat (minutes) | 48 | 80 |  | 8-12 Teams | 7
Total Mission Time (hours) | 2.3333 | 4.5 | 3.5 | 3.5 | 6 | 4.6667 | Match Time - Per Heat (hours) | 0.8 | 1.3333
[7 empty] | Match Time - Finals Bracket (minutes) | 42 | 60
Sample Agenda - No Lunch Break | [6 empty] | Match Time - Finals Bracket (hours) | 0.7 | 1
Activity | Start Time | End Time | Duration (hrs) |  |  |  | Total Match (hours) | 3.1 | 5
Team Check-in & Inspection | 8:00 | 8:30 | 0.5 |  |  |  | Tech Trials
Opening Ceremony | 8:30 | 9:00 | 0.5 |  |  |  | # Tech Trials / Team | 6 | 6
Mission Matches | 9:00 | 12:30 | 3.5 |  |  |  | Tech Trial Cycle Time (2 Tech Trials) | 6 | 4
Awards | 12:30 | 12:50 | 0.33333 |  |  |  | Tech Trial Fields | 1 | 2
Total Time | 4:50 | [5 empty] | Total Tech Trial Time (minutes) | 144 | 240
[7 empty] | Total Tech Trial Time (hours) | 2.4 | 4
Sample Agenda - Lunch Break | [6 empty] | Note: For teams to complete their Tech Trials for each Heat, the event must have the same number of Match and Tech Trial fields.
Activity | Start Time | End Time | Duration (hrs)
Team Check-in & Inspection | 8:00 | 8:30 | 0.5
Opening Ceremony | 8:30 | 9:00 | 0.5 |  |  |  | Sample Agenda - No Lunch Break
Mission Matches | 9:00 | 12:00 | 3 |  |  |  | Activity | Start Time | End Time | Duration (hrs) |  | Break Times (min)
Lunch Break | 12:00 | 12:30 | 0.5 |  |  |  | Team Check-in & Inspection | 8:00 | 8:30 | 0.5 |  | 10
Mission Matches | 12:30 | 14:00 | 1.5 |  |  |  | Opening Ceremony | 8:30 | 9:00 | 0.5 |  | Break Time (hrs)
Awards | 14:00 | 14:20 | 0.33333 |  |  |  | Matches & Tech Trials - Heat 1 | 9:00 | 10:00 | 1 |  | 0.16667
Total Time | 6:20 | [5 empty] | Break | 10:00 | 10:10 | 0.16667
[7 empty] | Matches & Tech Trials - Heat 2 | 10:10 | 11:10 | 1
[7 empty] | Break | 11:10 | 11:20 | 0.16667
[7 empty] | Matches & Tech Trials - Heat 3 | 11:20 | 12:20 | 1
[7 empty] | Break | 12:20 | 12:30 | 0.16667
[7 empty] | Finals Bracket | 12:30 | 13:12 | 0.7
[7 empty] | Break | 13:12 | 13:22 | 0.16667
[7 empty] | Awards | 13:22 | 13:42 | 0.33333
[7 empty] | Total Time | 5:42
Sample Agenda - Lunch Break
[7 empty] | Activity | Start Time | End Time | Duration (hrs)
[7 empty] | Team Check-in & Inspection | 8:00 | 8:30 | 0.5
[7 empty] | Opening Ceremony | 8:30 | 9:00 | 0.5
[7 empty] | Matches & Tech Trials - Heat 1 | 9:00 | 10:00 | 1
[7 empty] | Break | 10:00 | 10:10 | 0.16667
[7 empty] | Matches & Tech Trials - Heat 2 | 10:10 | 11:10 | 1
[7 empty] | Break | 11:10 | 11:20 | 0.16667
[7 empty] | Matches & Tech Trials - Heat 3 | 11:20 | 12:00 | 0.66667
[7 empty] | Lunch Break | 12:00 | 13:00 | 1
[7 empty] | Matches & Tech Trials - Heat 3 | 13:00 | 13:20 | 0.33333
[7 empty] | Break | 13:20 | 13:30 | 0.16667
[7 empty] | Finals Bracket | 13:30 | 14:12 | 0.7
[7 empty] | Break | 14:12 | 14:22 | 0.16667
[7 empty] | Awards | 14:22 | 14:42 | 0.33333
[7 empty] | Total Time | 6:42

## Event Checklist
Event Checklist
INITIAL PLANNING |  | ASSIGNED TO | NOTES
FALSE | Contact TEAM Alliance to inquire about hosting an event (support@teamalliance.org)
FALSE | Discuss what types of event(s) to host: - Program Types: SRM (indi, BOLT, RVR), SRC - Event Levels: Pre-Qualifying, Qualifying, and Championship Events
FALSE | Review the Event Host Support packages and Event Budget
FALSE | Estimate the event capacity for each program type
FALSE | Create a tentative event agenda and identify the setup day/time
FALSE | Identify core resources: - Volunteers / Staffing - Equipment - Venue
FALSE | Complete the Background Check (if needed)
FALSE | If available, take your event staff/volunteers to an event and shadow the roles. TEAM Alliance can assist with finding events and making an introduction.
FALSE | Develop a tentative layout of the event and equipment needed
FALSE | Determine if/how you will offer food or concessions
FALSE | Identify parking for event attendees
FALSE | Determine if the venue requires insurance, security or custodial services
FALSE | Post the event on myTEAMevents.org
TRAINING |  | ASSIGNED TO | NOTES
FALSE | Team Check-in volunteers review the volunteer role overview
FALSE | SRM Evaluators review the SRM Competition Manual and available training materials
FALSE | SRM Inspectors review the SRM Inspector volunteer role overview
FALSE | SRC Head Referees & Scorekeepers review the SRC Competition Manual and available training resources
FALSE | SRC Inspectors review the SRC Inspector volunteer role overview
FALSE | Emcee/Announcer reviews the volunteer role overview
FALSE | Queuer reviews the volunteer role overview
FALSE | Event Host and Event Technology Manager complete the competition application training
2 - 3 MONTHS PRIOR TO THE EVENT |  | ASSIGNED TO | NOTES
FALSE | Confirm the facility/venue reservation
FALSE | Review the registered team list with TEAM Alliance if there are any concerns about the event capacity
FALSE | Finalize the number of competition fields and game kits (SRC only) needed
FALSE | If receiving an Event Host Support package for competition equipment, awards and swag, verify with TEAM Alliance those items have been shipped.
FALSE | If borrowing competition fields, verify fields will be available for the event setup date.
FALSE | Confirm availability for all equipment needed for the event.
FALSE | Review final event layout with TEAM Alliance including, fields, displays, A/V, Team Check-in, Inspection, Queuing, and Team Staging
FALSE | Run through a practice event to verify venue WiFi and other technology functionality
FALSE | Create a plan for the concession stand and volunteer food / snacks, (if applicable)
FALSE | Identify and confirm event volunteers and set-up volunteers
FALSE | Order Referee / Volunteer shirts, if applicable
1 MONTH PRIOR TO THE EVENT |  | ASSIGNED TO | NOTES
FALSE | Reach out to TEAM Alliance to discuss any concerns or questions
FALSE | Review your event page and make any updates to the agenda, if needed
FALSE | Review the registered team list with TEAM Alliance if there are any concerns about the event capacity
FALSE | Discuss a safety plan with the venue owners and share it with local emergency and/or security providers
FALSE | If playing music, create a playlist that is appropriate for all ages and ensure proper licenses policies are followed
FALSE | Finalize event volunteers and verify they have completed their training
FALSE | Confirm Referee / Volunteer shirts have been delivered, if applicable
FALSE | Finalize and order/print any additional event signage
1-2 WEEKS PRIOR TO THE EVENT |  | ASSIGNED TO | NOTES
FALSE | Reach out to TEAM Alliance to discuss any concerns or questions. Verify that you have a TEAM Alliance phone number to call if any issues arise on the event day.
FALSE | Confirm the venue open and closing times to ensure availability
FALSE | Confirm concession stand details, if applicable
FALSE | Order volunteer / event staff food and beverages
FALSE | Send volunteers and teams an email with any relevant details about the event
FALSE | Purchase and organize supplies (pens, clipboards, stapler, Gaffers tape)
FALSE | Print paper scoresheets (if not using handheld tablets)
FALSE | Print a SRM and SRC Competition Manual for reference
FALSE | Print Inspection sheets (if not using laptops / tablets)
FALSE | Confirm all equipment needed (competition fields, A/V, tablets, tables, chairs, printer, laptops, extension cords, displays, etc.)
DAY PRIOR TO THE EVENT |  | ASSIGNED TO | NOTES
FALSE | Set up Team Staging area with tables, chairs, and power strips/extension cords
FALSE | Print Team Signs, if desired
FALSE | Set up Team Staging area with tables, chairs, and power strips/extension cords
FALSE | Set up Team Check-in table with a laptop / tablet to check-in teams
FALSE | Set up Inspection table(s) with the SRC sizing tool, printed inspection sheets or tablets/laptops
FALSE | Set up Competition Fields
FALSE | Print Field Signs and tape next to the field
FALSE | Set up Displays
FALSE | Set up Queuing tables and chairs
FALSE | Set up Volunteer / Printer Station
FALSE | If applicable set up stanchions to separate the audience area from the competition fields
FALSE | Ensure all cords are safely secured
FALSE | Post event signage
FALSE | Set up concession area, if applicable
FALSE | Verify trophies and medals are present
FALSE | Print out participation certificates, if applicable
FALSE | Test all A/V equipment and printer
FALSE | Ensure handheld tablets are charged
EVENT DAY |  | ASSIGNED TO | NOTES
FALSE | Open / unlock venue.
FALSE | Ensure restrooms are unlocked and stocked.
FALSE | Post any remaining event signage, if needed
FALSE | Set up volunteer snacks / beverages
FALSE | Finalize concession stand set up, if applicable
FALSE | Greet your volunteers and teams!
FALSE | Direct volunteers to their assigned areas and provide any last-minute training. Provide them with the event agenda and volunteer shirts, if applicable. If any volunteers do not attend, find replacements for these roles.
FALSE | Verify with the Team Check-in Volunteer that all teams are checked-in at least 10 minutes before the Opening Ceremony.
FALSE | Create and print the match schedule and remove any teams that are not checked-in and are not likely to attend.
FALSE | Conduct the Opening Ceremony and distribute match schedules.
FALSE | Check-in with the volunteers throughout the event to see if they have any questions or need a break.
FALSE | For SRC events, print out match schedules for Heats 2 and 3, when appropriate, and distribute to teams.
FALSE | After matches / missions have concluded, ensure the award winners are added correctly in the competition application, and print award ceremony scripts (or view on a tablet)
FALSE | Prepare Trophies and Medals for the Award ceremony
FALSE | Conduct the Awards Ceremony
FALSE | Thank your volunteers, teams, parents and sponsors for their support!
FALSE | Finalize the event in the competition application after the Award Ceremony is complete
FALSE | Tear down / clean up the venue

## Event Layouts
See this document:
Event Layouts